## Sheet1
Stuff We Need To Do			IGVC 2011
Category		Thing	Due Date
Mechanical		Purchase motors, wheels, tires, tubes, hubs	10/02/10
		Frame	10/23/10
		- CAD	10/02/10
		- Determine materials necessary	10/02/10
		- Purchase metal	10/09/10
		- Construct frame	10/23/10
		Integrate motors, wheels, frame	10/30/10
		3rd wheel
		Encoder mount

Software		Create classes for baseline with new JAUS structure	10/09/10
		Implement classes	10/16/10
		Interface with motor controller board	10/23/10
		Control loop	10/23/10
		State Machine (shouldn't be complicated)
		Vision Algorithms
		- Stereo Vision?
		LIDAR
		Sensor Fusion

Electrical		Motor controller board working on R/C	10/23/10
		Switching between R/C and PC control	10/30/10
		Microcontroller board	11/06/10
		- Status LEDs	11/06/10